CADENCE BY RECURSOCIAL

Cadence Build: Sections 2C through 2H Sequence

Six new kickoffs adding voice, email, cooldowns, master library, and compliance wiring.

Focus time: ~14 hours total focus time across 6 kickoffs    |    Estimated complexity: Mixed (Low to High)

## Why this sequence exists

The May 4 strategic review session locked decisions that go beyond the original Section 2B scope. Rather than expanding 2B mid-kickoff (which would invite scope drift), the new work lives in 2C through 2H. Each kickoff is sized to a 90-180 minute focus block.

Section 2B remains untouched and ships as scoped. 2C-2H follow after 2B is committed.

## Sequence and dependencies

| Kickoff | Title | Time | Depends on |
| --- | --- | --- | --- |
| 2C | Voice Architecture & Prompt Layer | 120 min | 2B complete |
| 2D | Email Infrastructure & Cadence Brief | 180 min | 2C |
| 2F | Cooldown Logic in Suggestion Engine | 90 min | 2C |
| 2G-1 | Master Library — Schema & Admin | 180 min | Consultant memo responses |
| 2G-2 | Master Library — Customer Onboarding | 150 min | 2G-1 |
| 2H | Compliance Engine Wiring | 150 min | 2C, 2G-1, consultant memo |

Notes on numbering: 2E was the originally-planned Cadence Insider kickoff. It is now deferred to post-launch and is not present in this sequence. The numbering jump from 2D to 2F preserves the original mental model.

## Parallel work tracks

Three tasks can run in parallel with the kickoffs above, since they are research/editorial and do not block code:

- Marketing Rules rebuild for High-risk products (~4 hours of ISI research). Can run any time after 2G-1 ships.

- Hook pruning from 300 to ~200 (~3 hours of editorial review). Can run any time after 2G-1 ships.

- Consultant memo responses incorporated. Triggers when responses arrive (target within 7 days of May 4).

## Total time and ordering

Total focus time across 2C-2H: roughly 14 hours. With Kevin reviewing each commit before merge, expect the full sequence to span 3-4 calendar weeks at typical pace.

Critical path: 2C → 2D → 2F (voice and email shipped). Then 2G-1 → 2G-2 (master library). Then 2H (compliance wiring). 2H is the last gate before Euphoria can be considered launch-ready.

## What is NOT in this sequence

- Cadence Insider monthly email — Phase 2 / post-launch.

- Audit log UI — Phase 2 / post-launch.

- Per-user publishing analytics — Phase 2 / post-launch.

- Customer brand voice editing UI — Phase 2 / post-launch.

- Layer B branded templates — separate track, sequenced after 2H.