CADENCE · NEXT STEPS DASHBOARD

The Euphoria Launch Sprint

Nine days. Six sessions. Twelve hours. One finished core.

Updated April 23, 2026

Target launch: Sunday, May 3, 2026

Pilot client: Euphoria Esthetics & Wellness, Barnegat NJ

# The strategic shift this dashboard captures

Three conversations reshaped the launch plan this session:

- Kevin articulated the Cadence core loop in its cleanest form to date — click Schedule My Week, Cadence recommends 4–6 specific reasoned posts, click any slot to open a branching wizard, answer 3–8 questions sized to post type, generated draft comes back for review and approval.

- Kevin confirmed the pilot must ship polished — not feature-complete. Brianna and Michelle are nurses running a med spa as their sole income source; the product must make them feel capable on first login, not overwhelmed. The 'still being built' perception would end the pilot.

- Kevin committed 12 hours over 9 days to get Cadence ready for Euphoria. This dashboard scopes exactly what gets built in those 12 hours — and equally importantly, what gets deferred.

The magic moment is clicking 'Schedule my week' and having five reasoned recommendations fill the calendar in under ten seconds. Everything else serves that moment.

# What's already built

Seventeen months of development, five completed priorities, live production data. This dashboard builds on — does not replace — the foundation already shipped.

### Shipped and live in production

| Priority | What ships today |
| --- | --- |
| P1 · Calendar | Weekly 7-day calendar, 7-type color system, click-to-create, post detail modal |
| P2 · Approvals | Submit for review, approval queue, approve/reject with notes, post_reviews audit trail |
| P3 · BEL | Email notifications, gap alerts, Monday digest, weekly execution scorecard |
| P4 · Publishing | Upload-Post integration, JWT connect, webhook receiver, approve-to-publish flow |
| P5 · RBAC | Owner / Admin / Staff roles, Team page, Christine & Ashley bootstrapped, dev user-switcher |
| P6 · Smart Content | PostWizard (8 post types), Event Campaign Engine, Trend Inbox, Anthropic SDK wired, GeneratedPostReview component |

Also live in production:

- 130 Euphoria services, 12 practitioners, 674 certifications imported

- Christine (Admin) and Ashley (Staff) bootstrapped in user_orgs

- GitHub repo RecurSocial/cadence-mvp — last commit f897606, Priority 6 complete

- Live app cadence-mvp.vercel.app, Supabase project nkjerngmimqkctmtecrc

# The gap · what stands between you and Euphoria

Seven items, sized honestly. One is a new build. Two are critical safety gates. Four are polish passes on surfaces already shipped.

| Type | Item | Estimated time |
| --- | --- | --- |
| BUILD · NEW | Schedule My Week endpoint + Monday Brief card + calendar populate | ~3 hrs |
| REFACTOR | PostWizard accepts postType prop and skips step 2 when pre-seeded from calendar click | ~1.5 hrs |
| POLISH · AI | Prompt engineering pass · Euphoria voice + service context + compliance awareness | ~2 hrs |
| POLISH · UI | Cadence brand system applied to dashboard, calendar, wizard, review screen | ~2 hrs |
| POLISH · COPY | Errors, empty states, loading messages rewritten as concierge, not server logs | ~1 hr |
| GATE · SAFETY | Dev user-switcher gated behind NEXT_PUBLIC_DEV_MODE env flag | ~30 min |
| GATE · INFRA | Rotate ANTHROPIC_API_KEY, update Vercel, confirm Euphoria OAuth path | ~30 min |
| TOTAL | Scoped work against a 12-hour budget | ~10.5 hrs |

The 1.5 hours of slack is not extra time. It's the buffer for surprises every solo build has. If scope creeps, cut brand repaint before cutting the prompt pass.

# Day one priority · rotate the Anthropic API key

Before any other work begins Friday morning, the Anthropic API key gets rotated. Rationale: recent industry reporting described API credential exposure through a third-party vendor environment and Claude Code vulnerabilities (CVE-2026-21852) that could exfiltrate keys from untrusted repositories. Precautionary rotation is good hygiene regardless of whether your specific key was exposed.

### Step-by-step · this is a Friday morning warm-up task

STEP 1 · ANTHROPIC CONSOLE

Open the Anthropic Console in your browser:

https://console.anthropic.com/settings/keys

- Click 'Create Key'

- Name it: cadence-production-2026-04-24

- Copy the new key to a secure temporary location — it will only be shown once

- Do NOT delete the old key yet. Wait until the new one is confirmed working.

STEP 2 · VERCEL

Open the Vercel dashboard in your browser:

https://vercel.com/recursocial/cadence-mvp/settings/environment-variables

- Find the existing ANTHROPIC_API_KEY variable

- Click the three dots next to it, select Edit

- Paste the new key value, save

- Ensure it is set for Production, Preview, AND Development environments (all three checkboxes)

STEP 3 · VERCEL · REDEPLOY

Go to the Deployments tab in Vercel:

https://vercel.com/recursocial/cadence-mvp/deployments

- Click the three dots on the most recent production deployment

- Select 'Redeploy'

- Uncheck 'Use existing Build Cache' to force a clean rebuild

- Click Redeploy, wait ~2 minutes for completion

STEP 4 · TEST THE NEW KEY

Visit cadence-mvp.vercel.app in your browser. Log in as Brianna via the dev user-switcher. Open the Content Calendar and click any empty day. Create a post using the wizard. If the generated post comes back successfully, the new key is live.

If you get a 401 Unauthorized error, the key was not saved correctly in Vercel. Go back to Step 2 and verify the value.

STEP 5 · ANTHROPIC CONSOLE · DELETE OLD KEY

Only after Step 4 succeeds, return to the Anthropic Console and delete the OLD key.

https://console.anthropic.com/settings/keys

- Identify the old key (created before April 24, 2026)

- Click the three dots, select Delete

- Confirm deletion

STEP 6 · LOCAL CURSOR · UPDATE .ENV.LOCAL

In Cursor, open the .env.local file at the root of your cadence-mvp project:

cd ~/cadence-mvp && open .env.local

- Update the ANTHROPIC_API_KEY value to match what's now in Vercel

- Save the file

- In your Terminal, restart the dev server:

npm run dev

- Confirm localhost:3000 loads correctly and AI generation works locally

Total time for API key rotation: 20-25 minutes. This is step zero of Friday's session.

# The nine-day sprint schedule

Six focused sessions. Twelve hours. A three-day mid-sprint rest that lets the work settle. A final polish day whose only job is making sure the product feels finished.

| Date | Hours | Focus |
| --- | --- | --- |
| Fri · Apr 24 | 2 | API key rotation · dev user-switcher gating · Schedule My Week backend endpoint |
| Sat · Apr 25 | 2 | Schedule My Week UI · Monday Brief card · wizard seeding from calendar click |
| Sun–Wed · Apr 26-29 | rest | No code. Log in as fresh Brianna daily. Note rough edges. Message Brianna and Michelle about OAuth weekend. |
| Thu · Apr 30 | 2 | Prompt engineering pass · Euphoria voice guide · service context injection · compliance framing |
| Fri · May 1 | 2 | Brand system repaint · Tailwind tokens · dashboard, calendar, wizard, review screen |
| Sat · May 2 | 2 | Copy polish · error messages · empty states · hide unfinished surfaces |
| Sun · May 3 | 2 | Fresh walkthrough with timer · fix final rough edges · deploy · text Brianna to schedule demo |

# Session-by-session breakdown

## Friday, April 24 · Session 1 · 2 hours

GOAL

API key rotated. Dev user-switcher gated. Schedule My Week backend endpoint returning reasoned recommendations.

PRE-SESSION CHECKLIST · BEFORE OPENING CURSOR

- Complete the API key rotation steps outlined in the Day One Priority section above (20-25 min)

- Send Brianna and Michelle a text: 'Cadence will be ready for you to try the weekend of May 3. I'll need 15 minutes to connect your Instagram and Facebook — can we pick a time Saturday May 2 or Sunday May 3?'

TASK 1 · CURSOR · GATE THE DEV USER-SWITCHER (20 MIN)

In Cursor, open the dev user-switcher component. Based on your project structure, this is likely at:

components/DevUserSwitcher.tsx

At the top of the component, add a conditional render based on an environment variable:

if (process.env.NEXT_PUBLIC_DEV_MODE !== 'true') return null;

Then in Terminal:

cd ~/cadence-mvp

echo 'NEXT_PUBLIC_DEV_MODE=true' >> .env.local

In Vercel dashboard → Environment Variables: add NEXT_PUBLIC_DEV_MODE=false for Production only. Leave it unset for Preview and Development. This means the switcher works on localhost and Preview but disappears on the production cadence-mvp.vercel.app URL.

TASK 2 · CURSOR · CREATE SCHEDULE MY WEEK API ROUTE (90 MIN)

In Cursor, create the new API route file:

app/api/cadence/schedule-week/route.ts

The endpoint accepts a POST request with org_id and week_start. It reads the cadence_plan, pulls the service catalog and practitioner list, builds a prompt asking Claude to recommend 5 specific posts for the week with reasoning, and returns an array of suggested posts with scheduled_time, post_type, topic_hint, and reasoning fields.

- Input: { org_id, week_start }

- Process: fetch cadence_plan + services + practitioners from Supabase

- Process: call Anthropic with structured prompt asking for 5 reasoned post recommendations

- Output: array of { scheduled_day, scheduled_time, post_type, topic_hint, reasoning }

Deliverable at end of session: API route deployed, testable via Postman or curl, returns 5 recommendations for Euphoria's current week.

TASK 3 · TERMINAL · COMMIT AND DEPLOY (10 MIN)

cd ~/cadence-mvp

git add .

git commit -m "Friday sprint: API key rotation, dev gate, schedule-week endpoint"

git push origin main

Vercel auto-deploys on push. Verify deployment succeeds before ending the session.

## Saturday, April 25 · Session 2 · 2 hours

GOAL

Monday Brief card with working Schedule My Week button. Calendar populates with suggested slots. Clicking a slot opens the wizard pre-seeded with the correct post type.

TASK 1 · CURSOR · BUILD MONDAY BRIEF CARD (45 MIN)

In Cursor, create a new component:

components/MondayBrief.tsx

Place it above the WeeklyCalendarView on the dashboard page. Two states: empty week (shows 'Schedule my week' button) and populated week (shows scorecard summary). Use the editorial treatment from the mockup earlier in this project — serif headline, champagne button, single clear CTA.

TASK 2 · CURSOR · WIRE SCHEDULE MY WEEK BUTTON TO THE ENDPOINT (30 MIN)

On button click, fetch the schedule-week endpoint built Friday. On success, create draft posts in Supabase for each recommendation. Show a loading state with the message 'Building your week…' for 5-10 seconds while generation runs. On completion, refresh the calendar view.

TASK 3 · CURSOR · UPDATE WEEKLYCALENDARVIEW TO SHOW SUGGESTED SLOTS (30 MIN)

Suggested posts need a distinct visual treatment from user-created posts. Gold left border, slightly lighter fill, small 'Suggested' badge. Clicking a suggested slot opens PostWizard with props:

<PostWizard postType={suggestion.post_type} suggestedTime={suggestion.scheduled_time} reasoning={suggestion.reasoning} />

TASK 4 · CURSOR · REFACTOR POSTWIZARD TO ACCEPT PRE-SEEDED POST TYPE (15 MIN)

Current PostWizard has Step 1 (platform) and Step 2 (post type selection). When opened with a postType prop, skip Step 2 and jump directly to Step 3 branch questions. Show the pre-selected post type as a read-only header at the top.

## Sunday–Wednesday, April 26–29 · Rest days

No code this stretch. Deliberately. Two things to do instead:

- Every evening, log in as fresh Brianna (dev switcher on localhost). Click through the flow. Note anything that feels rough, confusing, slow, or embarrassing. Build a list. That list becomes your Saturday May 2 polish target.

- Follow up on the OAuth scheduling message with Brianna and Michelle. Confirm a time. Whatever time they pick, that's your hard deadline for 'Cadence ready to demo.'

The best polish ideas come from distance, not keyboard time.

## Thursday, April 30 · Session 3 · 2 hours

GOAL

The generated post quality jumps from 'decent' to 'better than what Brianna would write in 30 seconds.'

PRE-SESSION HOMEWORK · 45 MINUTES EARLIER IN THE DAY

- Write a one-paragraph Euphoria voice guide. What does Euphoria sound like? Warm but expert. Educational without being preachy. Confident about results without overpromising. Brianna and Michelle's voice, not a corporate med spa voice.

- Pull 5 examples of the best Instagram captions Euphoria has ever posted (from the three months you audited earlier)

- Pull 5 examples of captions from competing med spas that feel generic or cringe — the opposite of what you want

TASK 1 · CURSOR · FIND AND OPEN THE GENERATE-POST ROUTE (10 MIN)

app/api/generate-post/route.ts

Locate the system prompt. This is the paragraph of instructions Claude receives before generating any post.

TASK 2 · CURSOR · REWRITE THE SYSTEM PROMPT (70 MIN)

The new system prompt should include, in order:

- Role framing: you are writing social media content for Euphoria Esthetics & Wellness, a med spa in Barnegat NJ owned by two experienced nurses (Brianna, NP, and Michelle, RN)

- Voice guide: paste the paragraph written during pre-session homework

- Good/bad examples: include all 10 examples with clear labels

- Service context injection: dynamically include the selected service's full details from Supabase (description, indication, downtime, typical candidate, price range)

- Practitioner context injection: if a practitioner was named in the wizard, include their specialty and lane

- Medical aesthetics compliance awareness: never promise specific results, avoid 'miracle' language, include a consultation CTA for any treatment-related post

- Output format: headline (under 10 words), caption (2-3 paragraphs, conversational), 6-10 hashtags (mix of branded, service-specific, and local)

TASK 3 · TEST ALL 8 POST TYPES AGAINST REAL EUPHORIA SERVICES (40 MIN)

In a browser, log into localhost:3000. Run the wizard for each of the 8 post types using real Euphoria services. For each:

- Screenshot the generated post

- Ask yourself: would this make Brianna say 'holy shit, this is better than what I'd write'?

- If yes, move on. If no, tweak the prompt and re-test.

## Friday, May 1 · Session 4 · 2 hours

GOAL

The four core surfaces look like Cadence. Not indigo/slate SaaS. Champagne, cream, graphite luxury.

TASK 1 · CURSOR · UPDATE TAILWIND CONFIG (15 MIN)

tailwind.config.js

Replace the existing color tokens with the Cadence palette. The exact config is in your Cadence brand system reference (visual-system.md). Add the typography configuration to pull in Playfair Display from Google Fonts as the serif family.

TASK 2 · CURSOR · REPAINT THE FOUR CORE SURFACES (90 MIN)

- Dashboard · 25 min · convert background to cream, sidebar to bone, cards to white-on-bone with sand borders

- Weekly Calendar · 25 min · replace indigo post-type colors with champagne/gold accent system, serif day headers

- PostWizard · 20 min · questions in sans, headers in serif, champagne button for primary action

- GeneratedPostReview · 20 min · editorial layout, generous whitespace, serif headline over the generated caption

TASK 3 · CURSOR · HIDE SURFACES NOT READY FOR PILOT (15 MIN)

- Billing pages · comment out the nav link, keep code intact

- Analytics pages · comment out the nav link

- Any 'Coming soon' placeholders · remove, don't hide

The sidebar should have exactly four items after this session: Calendar, Drafts, Approvals, Team. Settings sits under a user menu in the top-right.

## Saturday, May 2 · Session 5 · 2 hours

GOAL

Every word Brianna will read is written by a concierge, not a server log.

TASK 1 · CURSOR · GLOBAL SEARCH FOR COMMON ROUGH COPY (60 MIN)

- Search for 'Something went wrong' · rewrite each instance specific to what actually went wrong, with a suggested next action

- Search for 'No [X] yet' · rewrite as editorial empty states with a single suggested action

- Search for 'Loading...' · replace with specific messages: 'Building your week...', 'Writing your draft...', 'Saving your work...'

- Search for 'Error' in toast/alert components · soften to plain English

TASK 2 · CURSOR · EMPTY STATE DESIGN PASS (30 MIN)

The three most important empty states:

- Empty calendar with no posts scheduled → the Monday Brief card with Schedule My Week button

- Empty approvals queue → 'Everything's reviewed. Michelle, you can close this tab.'

- Empty drafts folder → 'No drafts waiting. Great week so far.'

TASK 3 · CURSOR · THE OAUTH CONNECTION MOMENT (30 MIN)

When Brianna and Michelle log in the weekend of May 3, their social accounts won't be connected. The first thing they'll see should be a calm invitation to connect — not a giant red warning banner. Design this moment specifically:

- Header card: 'Let's connect your accounts.' Serif, large, calm.

- Body: 'Cadence needs access to your Instagram, Facebook, and TikTok to schedule posts. This takes about 90 seconds.'

- Single button: 'Connect accounts →' opens the Upload-Post OAuth flow

- Dismissable: 'I'll do this later' closes the card, they can still explore the product

## Sunday, May 3 · Session 6 · 2 hours

GOAL

The fresh walkthrough. The one you do at the end of every sprint but never actually do. Today you do it.

TASK 1 · SIMULATE BRIANNA'S FIRST 15 MINUTES (45 MIN)

- Close Cursor. Close Terminal. Open only a browser. Log into cadence-mvp.vercel.app as Brianna via the dev switcher.

- Start a timer. Goal: go from empty week to 5 submitted drafts in under 15 minutes.

- Take notes on every rough edge, every moment of hesitation, every place the copy felt off, every place the design broke.

TASK 2 · CURSOR · FIX THE ROUGH EDGES (60 MIN)

Work through the list from Task 1 in order of 'how much would this embarrass me.' Fix the top 5-8 items. Anything that takes more than 10 minutes gets logged for a future session — this is triage, not perfection.

TASK 3 · TERMINAL · FINAL DEPLOY (10 MIN)

cd ~/cadence-mvp

git add .

git commit -m "Euphoria launch sprint complete · ready for pilot"

git push origin main

TASK 4 · TEXT BRIANNA TO SCHEDULE THE DEMO (5 MIN)

Suggested message:

Cadence is ready. I want to show you and Michelle how it works — can we spend 30 minutes together? I'll walk you through the Monday routine, then you try it yourself. Pick a time this week that works.

# Risks & guardrails

### What could kill this sprint

- Scope creep · adding 'just one more thing' during build sessions. Counter: every session has a defined scope above. Anything outside scope gets logged to a 'post-Euphoria' list.

- Prompt engineering failure · the generated posts don't land. Counter: come to Thursday's session with the pre-session homework done. This is the single highest-leverage session in the sprint.

- Perfectionism on brand repaint · spending 4 hours on what should be 2. Counter: if the Friday May 1 session runs over, accept the UI as 'good enough' and move on. Ugly-but-working beats pretty-but-missing.

- OAuth delay from Brianna/Michelle · if they can't connect social accounts by May 3, the demo still happens, but without live publishing. That's survivable — the core loop works regardless.

### What must not break

- Dev user-switcher visible in production · catastrophic for the 'built for us' illusion. Gate this Friday morning.

- Generated post quality falls below 'better than Brianna would write in 30 seconds' · then Cadence is just a scheduler and the pitch dies

- The Schedule My Week button takes more than 10 seconds to respond · then the magic moment becomes a loading screen moment

# What ships · what waits

| Ships for Euphoria May 3 | Waits until after pilot validation |
| --- | --- |
| Schedule My Week · Monday Brief card | Wizard question tiering (light/medium/deep) |
| 8-type PostWizard (existing) | 'Why these picks?' reasoning layer surfaced to user |
| Event Campaign Engine (existing) | Compliance layer for Promotional/Event posts |
| Trend Inbox (existing) | Analytics dashboard (Priority 7) |
| Approval workflow (existing) | Stripe billing (Priority 8) |
| Upload-Post integration (existing) | Stock photo suggestions (Priority 9) |
| Cadence brand system applied | Post Builder · B&A composer (Priority 10) |
| Concierge-written copy throughout | Canva integration (explicitly declined) |
| Euphoria OAuth live publishing | AI image generation (explicitly declined for MVP) |

# Key technical facts

| Live App URL | cadence-mvp.vercel.app |
| --- | --- |
| GitHub Repo | github.com/RecurSocial/cadence-mvp |
| Last Commit | f897606 — Priority 6 complete (April 18, 2026) |
| Supabase Project | nkjerngmimqkctmtecrc.supabase.co |
| Euphoria Org UUID | 74b04f56-8cf0-7427-b977-7574b183226d |
| Email Sender | noreply@notifications.cadencesocial.io |
| Publishing API | Upload-Post (MVP) — migrate to Ayrshare at 100 customers |
| AI Model | claude-sonnet-4-5 via Anthropic API |
| Tech Stack | Next.js + Supabase + Vercel + Resend + Upload-Post + Stripe |
| Dev Server | cd ~/cadence-mvp && npm run dev → localhost:3000 |
| Node Version | v24.14.1 |

RecurSocial LLC · Cadence Platform

Next Steps Dashboard · Euphoria Launch Sprint · April 23, 2026

Confidential & Proprietary